## Sheet1
Risk ID | Category | Risk Description | Probability | Impact | Risk Score | Mitigation Strategy | Indicator | Contingency Plan | Responsible | Status | Last modifed date
1 | Organization | Key team member gets sick for a while | 3 | 9 | 27 | Reduce workload for the specified timeperiod. If possible, fill the gap that occurs, while member is absent. | Member not in classrorom | Conduct exit interviews, establish talent pipelines, and provide onboarding support to new employees | Team | Open | 2023-04-02
2 | Project | Laptop malfunctions | 2 | 7 | 14 | Have an alternative laptop at hand. | Bluescreen | Switch to a different device and set up versioning on the new laptop | Team | Closed | 2023-04-12
4 | Legal | Unexpected changes in school regulations | 3 | 4 | 12 | Monitor regulatory changes, get information from the school itself | Discussion in classroom, on moodle and on social media | Take actions according to the regulations | Team | Open | 2023-04-12
5 | Technical | Godot releases uncompamtible updates | 5 | 10 | 50 | Rule out the possible compatibility problems that could occur | Game not starting. Objects won’t be rendered. Compilation error. | Quickly secure compatibility by researching possible solutions. | Team | Open | 2023-04-12
6 | Technical | Bad estimation of performance | 3 | 7 | 21 | Have an emulator at hand to test the performance issues on multiple devices. | Lagging, launching issues | Identify safe areas for evacuation, establish communication protocols, and maintain an emergency kit with essential supplies | Team | Open | 2023-04-12
7 | Legal | Licensing issues | 2 | 3 | 6 | Checking license issues in review steps. | Indicator for licensing shows up | Search for and use alternatives for the issued components. | Team | Closed | 2023-04-12
8 | Technical | Bad performance of new function | 3 | 8 | 24 | Test the new functions for performance (on multiple devices) before publishing | Performance drop after changes, lag | Dont release new feature that causes problems, investigate where performance lags, find alternative, faster implementation possibilities | Team | Open | 2023-04-12
9 | Project | Natural disasters | 1 | 10 | 10 | Checking the news and getting information on a regular basis | Depends on the natural disaster itself | Uphold communication with digital tools if possible. Go to evacuation sites. | Organisation | Open | 2023-04-12
10 | Organization | Inadequate knowledge | 4 | 7 | 28 | Prepare for new versions of the software components. | Long research times, wrong implementation | Research, watch tutorials and / or reduce feature scope | Team | Closed | 2023-04-12